## WBS_ECKERS
ID | #VALUE! |  | Editable User Area |  |  | #VALUE! | Progress Bar | Days | Work Days | Summary Task | Parent | Children | Options | Backup | 2020 | [28 empty] | 2020 | [30 empty] | 2020 | [29 empty] | 2020 | [30 empty] | 2020 | [29 empty] | 2020 | [30 empty] | 2020 | [30 empty] | 2020 | [29 empty] | 2020 | [30 empty] | 2020 | [29 empty] | 2020 | [30 empty] | 2021 | [30 empty] | 2021 | [27 empty] | 2021 | [30 empty] | 2021 | [29 empty] | 2021 | [30 empty] | 2021 | [29 empty] | 2021 | [30 empty] | 2021 | [30 empty] | 2021 | [29 empty] | 2021 | [30 empty] | 2021 | [29 empty] | 2021 | [30 empty] | 2022 | [30 empty] | 2022 | [27 empty] | 2022 | [30 empty] | 2022 | [29 empty] | 2020 | [9 empty] | 2020 | [12 empty] | 2020 | [12 empty] | 2020 | [12 empty] | 2021 | [12 empty] | 2021 | [12 empty] | 2021 | [12 empty] | 2021 | [12 empty] | 2022 | [12 empty] | 2022 | [5 empty] | 2020 |  |  | 2020 |  |  | 2020 |  |  | 2021 |  |  | 2021 |  |  | 2021 |  |  | 2021 |  |  | 2022 |  |  | 2022
[15 empty] | February | [28 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [30 empty] | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [30 empty] | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | January | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April
| Work Breakdown Structure | Start | End | Person | Progress | Dependency | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
[15 empty] | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M
1 | Project Plannig | 2020-04-09 | 2020-06-18 |  | 0% |  |  | 71 | 51 | x |  |  | ["Activate PRO features"] | ["1","Project Plannig","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""] | bar: April 9 T to June 18 T; April 15 M to June 25 M
1.1 | Project Vision | 2020-04-09 | 2020-06-18 |  | 0% |  |  | 71 | 51 | x |  |  | ["Activate PRO features"] | ["1.1"," Project Vision ","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""] | bar: April 9 T to June 18 T; April 15 M to June 25 M
1.1.1 | Meeting with the Stakeholders | 2020-04-09 | 2020-06-18 |  | 0% |  |  | 71 | 51 |  |  |  | ["Activate PRO features"] | ["1.1.1"," Meeting with the Stakeholders","","","","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: April 9 T to June 18 T; April 15 M to June 25 M
1.1.2 | End User goal Analysis | 2020-04-15 | 2020-04-23 |  | 0% |  |  | 9 | 7 |  |  |  | ["Activate PRO features"] | ["1.1.2"," End User goal Analysis","","","","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: April 15 W to April 23 T; April 16 M to April 17 M
1.1.3 | Create a Finance Plan | 2020-04-24 | 2020-04-26 |  | 0% |  |  | 3 | 1 |  |  |  | ["Activate PRO features"] | ["1.1.3"," Create a Finance Plan","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""] | bar: April 24 F to April 26 S; April 17 M
1.2 | Manage Communication Plan | 2020-04-15 | 2020-04-17 |  | 0% |  |  | 3 | 3 |  |  |  | ["Activate PRO features"] | ["1.2"," Manage Communication Plan","","","","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: April 15 W to April 17 F; April 16 M
1.3 | Manage Integration Planning | 2020-04-09 | 2020-04-09 |  | 0% |  |  | 1 | 1 |  |  |  | ["Activate PRO features"] | ["1.3"," Manage Integration Planning","","","","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: April 9 T; April 15 M
1.4 | Project Plan Document |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["1.4"," Project Plan Document","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
1.5 | Analysis | 2020-05-04 | 2020-06-18 |  | 0% |  |  | 46 | 34 | x |  |  | ["Activate PRO features"] | ["1.5"," Analysis",1588550400000,1592438400000,"",0,"","","","","x","","","[\"Activate PRO features\"]","","",""] | bar: May 4 M to June 18 T; May 19 M to June 25 M
1.5.1 | Risk Analysis | 2020-06-18 | 2020-06-18 |  | 0% |  |  | 1 | 1 |  |  |  | ["Activate PRO features"] | ["1.5.1"," Risk Analysis",1592438400000,1592438400000,"",0,"","","","","","","","[\"Activate PRO features\"]","","",""] | bar: June 18 T; June 25 M
1.5.2 | Requirement Gathering | 2020-05-04 | 2020-05-13 |  | 0% |  |  | 10 | 8 |  |  |  | ["Activate PRO features"] | ["1.5.2"," Requirement Gathering",1588550400000,1589328000000,"",0,"","","","","","","","[\"Activate PRO features\"]","","",""] | bar: May 4 M to May 13 W; May 19 M to May 20 M
1.5.3 | Class Analysis | 2020-05-15 | 2020-05-18 |  | 0% |  |  | 4 | 2 |  |  |  | ["Activate PRO features"] | ["1.5.3"," Class Analysis",1589500800000,1589760000000,"",0,"","","","","","","","[\"Activate PRO features\"]","","",""] | bar: May 15 F to May 18 M; May 20 M to May 21 M
1.5.4 | Architecutre Anaylsis | 2020-05-15 | 2020-06-18 |  | 0% |  |  | 35 | 25 |  |  |  | ["Activate PRO features"] | ["1.5.4"," Architecutre Anaylsis",1589500800000,1592438400000,"",0,"","","","","","","","[\"Activate PRO features\"]","","",""] | bar: May 15 F to June 18 T; May 20 M to June 25 M
1.6 | Analysis Document |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["1.6"," Analysis Document","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
1.7 | Create a Design Plan | 2020-05-04 | 2020-06-18 |  | 0% |  |  | 46 | 34 | x |  |  | ["Activate PRO features"] | ["1.7"," Create a Design Plan",1588550400000,1592438400000,"",0,"","","","","x","","","[\"Activate PRO features\"]","","",""] | bar: May 4 M to June 18 T; May 19 M to June 25 M
1.7.1 | Design User Stories | 2020-05-04 | 2020-05-13 |  | 0% |  |  | 10 | 8 |  |  |  | ["Activate PRO features"] | ["1.7.1"," Design User Stories",1588550400000,1589328000000,"",0,"","","","","","","","[\"Activate PRO features\"]","","",""] | bar: May 4 M to May 13 W; May 19 M to May 20 M
1.7.2 | Design Screen | 2020-05-10 | 2020-05-20 |  | 0% |  |  | 11 | 8 |  |  |  | ["Activate PRO features"] | ["1.7.2"," Design Screen",1589068800000,1589932800000,"",0,"","","","","","","","[\"Activate PRO features\"]","","",""] | bar: May 10 S to May 20 W; May 19 M to May 21 M
1.7.3 | Design Class | 2020-05-21 | 2020-05-24 |  | 0% |  |  | 4 | 2 |  |  |  | ["Activate PRO features"] | ["1.7.3"," Design Class",1590019200000,1590278400000,"",0,"","","","","","","","[\"Activate PRO features\"]","","",""] | bar: May 21 T to May 24 S; May 21 M
1.7.4 | Design DB | 2020-05-15 | 2020-05-17 |  | 0% |  |  | 3 | 1 |  |  |  | ["Activate PRO features"] | ["1.7.4"," Design DB",1589500800000,1589673600000,"",0,"","","","","","","","[\"Activate PRO features\"]","","",""] | bar: May 15 F to May 17 S; May 20 M
1.7.5 | Design Architecture | 2020-05-18 | 2020-06-18 |  | 0% |  |  | 32 | 24 |  |  |  | ["Activate PRO features"] | ["1.7.5"," Design Architecture",1589760000000,1592438400000,"",0,"","","","","","","","[\"Activate PRO features\"]","","",""] | bar: May 18 M to June 18 T; May 21 M to June 25 M
1.8 | Product Design Document |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["1.8"," Product Design Document","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
1.9 | Design Tests | 2020-06-01 | 2020-06-03 |  | 0% |  |  | 3 | 3 | x |  |  | ["Activate PRO features"] | ["1.9"," Design Tests","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
1.9.1 | Design Manual Tests | 2020-06-01 | 2020-06-03 |  | 0% |  |  | 3 | 3 |  |  |  | ["Activate PRO features"] | ["1.9.1"," Design Manual Tests","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
1.10 | Test Design Document |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["1.10"," Test Design Document","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
2 | Kick off Meeting | 2020-04-09 | 2020-06-07 |  | 0% |  |  | 60 | 42 | x |  |  | ["Activate PRO features"] | ["2","Kick off Meeting","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
2.1 | Develop Product Backlog |  |  |  | 0% |  |  |  |  | x |  |  | ["Activate PRO features"] | ["2.1"," Develop Product Backlog","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
2.1.1 | User Stories Correction | 2020-05-13 | 2020-05-13 |  | 0% |  |  | 1 | 1 |  |  |  | ["Activate PRO features"] | ["2.1.1"," User Stories Correction","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
2.1.2 | Written product backlog | 2020-06-04 | 2020-06-06 |  | 0% |  |  | 3 | 2 |  |  |  | ["Activate PRO features"] | ["2.1.2"," Written product backlog","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
2.1.3 | Feedback and closure | 2020-06-07 | 2020-06-07 |  | 0% |  |  | 1 | 0 |  |  |  | ["Activate PRO features"] | ["2.1.3"," Feedback and closure","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
2.2 | Product Backlog |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["2.2"," Product Backlog","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
3 | Working Envoimment Setup | 2020-06-08 | 2020-06-10 |  | 0% |  |  | 3 | 3 | x |  |  | ["Activate PRO features"] | ["3","Working Envoimment Setup","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
3.1 | Setup PC for Development | 2020-06-08 | 2020-06-08 |  | 0% |  |  | 1 | 1 |  |  |  | ["Activate PRO features"] | ["3.1"," Setup PC for Development","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
3.2 | Setup testing environment | 2020-06-09 | 2020-06-09 |  | 0% |  |  | 1 | 1 |  |  |  | ["Activate PRO features"] | ["3.2"," Setup testing environment","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
3.3 | Setup servers | 2020-06-10 | 2020-06-10 |  | 0% |  |  | 1 | 1 |  |  |  | ["Activate PRO features"] | ["3.3"," Setup servers","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
3.4 | Environment Setup Document |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["3.4"," Environment Setup Document","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4 | Development | 2020-06-19 | 2021-05-18 |  | 0% |  |  | 334 | 238 | x |  |  | ["Activate PRO features"] | ["4","Development","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
4.1 | AI Development | 2020-06-19 | 2021-03-18 |  | 0% |  |  | 273 | 195 | x |  |  | ["Activate PRO features"] | ["4.1"," AI Development","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
4.1.1 | Sprint 1 : Grammar and Pronunciation Correction Functions | 2020-06-19 | 2021-03-18 |  | 0% |  |  | 273 | 195 | x |  |  | ["Activate PRO features"] | ["4.1.1"," Sprint 1 : Grammar and Pronunciation Correction Functions","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
4.1.1.1 | Daily standup Meeting |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.1.1.1"," Daily standup Meeting","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.1.1.2 | Korean |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.1.1.2"," Korean","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.1.1.3 | Japanese |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.1.1.3"," Japanese","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.1.1.4 | French |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.1.1.4"," French","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.1.1.5 | Prototype Deployment |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.1.1.5"," Prototype Deployment","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.1.1.6 | Sprint Review Meeting |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.1.1.6"," Sprint Review Meeting","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.1.1.7 | AI developed With Documentation |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.1.1.7"," AI developed With Documentation","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.2 | UI/UX Design | 2020-06-19 | 2020-07-18 |  | 0% |  |  | 30 | 21 | x |  |  | ["Activate PRO features"] | ["4.2"," UI/UX Design","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
4.2.1 | Sprint 2 : Web Front End | 2020-06-19 | 2020-07-18 |  | 0% |  |  | 30 | 21 | x |  |  | ["Activate PRO features"] | ["4.2.1"," Sprint 2 : Web Front End","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
4.2.1.1 | Daily standup Meeting |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.2.1.1"," Daily standup Meeting","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.2.1.2 | Development and Testing |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.2.1.2"," Development and Testing","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.2.1.3 | Prototype Deployment |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.2.1.3"," Prototype Deployment","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.2.1.4 | Sprint Review Meeting |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.2.1.4"," Sprint Review Meeting","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.2.1.5 | Front End developed With Documentation |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.2.1.5"," Front End developed With Documentation","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.2.2 | Sprint 3 : App Front End | 2020-06-19 | 2020-07-18 |  | 0% |  |  | 30 | 21 | x |  |  | ["Activate PRO features"] | ["4.2.2"," Sprint 3 : App Front End","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
4.2.2.1 | Daily standup Meeting |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.2.2.1"," Daily standup Meeting","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.2.2.2 | Development and Testing |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.2.2.2"," Development and Testing","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.2.2.3 | Prototype Deployment |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.2.2.3"," Prototype Deployment","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.2.2.4 | Sprint Review Meeting |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.2.2.4"," Sprint Review Meeting","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.2.2.5 | Front End developed With Documentation |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.2.2.5"," Front End developed With Documentation","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.3 | Function Development | 2020-06-19 | 2021-03-18 |  | 0% |  |  | 273 | 195 | x |  |  | ["Activate PRO features"] | ["4.3"," Function Development","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
4.3.1 | Sprint 4 : Function | 2020-06-19 | 2021-03-18 |  | 0% |  |  | 273 | 195 | x |  |  | ["Activate PRO features"] | ["4.3.1"," Sprint 4 : Function","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
4.3.1.1 | Daily standup Meeting |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.3.1.1"," Daily standup Meeting","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.3.1.2 | Grammar Correction Function |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.3.1.2"," Grammar Correction Function","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.3.1.3 | Pronunciation Correction Function |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.3.1.3"," Pronunciation Correction Function","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.3.1.4 | Shadowing Contents Function |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.3.1.4"," Shadowing Contents Function","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.3.1.5 | Level Test Function |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.3.1.5"," Level Test Function","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.3.1.6 | User Matching Function |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.3.1.6"," User Matching Function","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.3.1.7 | Prototype Deployment |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.3.1.7"," Prototype Deployment","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.3.1.8 | Sprint Review Meeting |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.3.1.8"," Sprint Review Meeting","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.3.1.9 | Function developed With Documentation |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.3.1.9"," Function developed With Documentation","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.4 | Database Development | 2020-06-19 | 2020-12-18 |  | 0% |  |  | 183 | 131 | x |  |  | ["Activate PRO features"] | ["4.4"," Database Development","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
4.4.1 | Sprint 5 : Setup Database | 2020-06-19 | 2020-12-18 |  | 0% |  |  | 183 | 131 | x |  |  | ["Activate PRO features"] | ["4.4.1"," Sprint 5 : Setup Database","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
4.4.1.1 | Daily standup Meeting |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.4.1.1"," Daily standup Meeting","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.4.1.2 | Development |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.4.1.2"," Development","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.4.1.3 | Testing |  |  |  | 0% |  |  |  |  | x |  |  | ["Activate PRO features"] | ["4.4.1.3"," Testing","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
4.4.1.3.1 | System Testing |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.4.1.3.1"," System Testing","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.4.1.4 | Deployment |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.4.1.4"," Deployment","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.4.1.5 | Sprint Review Meeting |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.4.1.5"," Sprint Review Meeting","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
4.4.1.6 | Database Module of user tracking is developed |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["4.4.1.6"," Database Module of user tracking is developed","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
5 | Production Testing & Deployment | 2021-03-19 | 2021-03-28 |  | 0% |  |  | 10 | 6 | x |  |  | ["Activate PRO features"] | ["5","Production Testing & Deployment","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
5.1 | Testing | 2021-03-19 | 2021-03-21 |  | 0% |  |  | 3 | 1 | x |  |  | ["Activate PRO features"] | ["5.1"," Testing","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
5.1.1 | Integration test |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["5.1.1"," Integration test","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
5.1.2 | Quality management and feedback |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["5.1.2"," Quality management and feedback","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
5.1.3 | Test Report |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["5.1.3"," Test Report","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
5.2 | Deployment | 2021-03-22 | 2021-03-28 |  | 0% |  |  | 7 | 5 | x |  |  | ["Activate PRO features"] | ["5.2"," Deployment","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
5.2.1 | Create and share scenario |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["5.2.1"," Create and share scenario","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
5.2.2 | Notice |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["5.2.2"," Notice","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
5.2.3 | Deployment/Preparing of Failover |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["5.2.3"," Deployment/Preparing of Failover","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
5.2.4 | Server Transfer |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["5.2.4"," Server Transfer","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
5.2.5 | Deployment Report |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["5.2.5"," Deployment Report","","","",0,"","","","","","","","[\"Activate PRO features\"]","","",""]
6 | Project Closing | 2021-03-29 | 2021-04-11 |  | 0% |  |  | 14 | 10 | x |  |  | ["Activate PRO features"] | ["6","Project Closing","","","",0,"","","","","x","","","[\"Activate PRO features\"]","","",""]
6.1 | Execute Closing procedure |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["6.1"," Execute Closing procedure","","","","","","","","","","","","[\"Activate PRO features\"]","","",""]
6.2 | Project Delievered |  |  |  | 0% | [7 empty] | ["Activate PRO features"] | ["6.2"," Project Delievered","","","","","","","","","","","","[\"Activate PRO features\"]","","",""]