## Please wait...
ID | ECKERS_WBS | [6 empty] | 2021 |  |  | 2021 |  |  | 2022 |  |  | 2022
[6 empty] | May | June | July | August | September | October | November | December | January | February | March | April
| Work Breakdown Structure | Start | End | Progress | Dependency
1 | Project Plannig | 2020-04-09 | 2020-06-18 | 0% | Initial Phase
1.1 | Project Vision | 2020-04-09 | 2020-06-18 | 0%
1.1.1 | Meeting with the Stakeholders | 2020-04-09 | 2020-06-18 | 0%
1.1.2 | End User goal Analysis | 2020-04-15 | 2020-04-23 | 0%
1.1.3 | Create a Finance Plan | 2020-04-24 | 2020-04-26 | 0%
1.2 | Manage Communication Plan | 2020-04-15 | 2020-04-17 | 0%
1.3 | Manage Integration Planning | 2020-04-09 | 2020-04-09 | 0%
1.4 | Project Plan Document |  |  | 0%
1.5 | Analysis | 2020-05-04 | 2020-06-18 | 0% | Project Vision
1.5.1 | Risk Analysis | 2020-06-18 | 2020-06-18 | 0%
1.5.2 | Requirement Gathering | 2020-05-04 | 2020-05-13 | 0%
1.5.3 | Class Analysis | 2020-05-15 | 2020-05-18 | 0%
1.5.4 | Architecutre Anaylsis | 2020-05-15 | 2020-06-18 | 0%
1.6 | Analysis Document |  |  | 0%
1.7 | Create a Design Plan | 2020-05-04 | 2020-06-18 | 0% | Analysis
1.7.1 | Design User Stories | 2020-05-04 | 2020-05-13 | 0%
1.7.2 | Design Screen | 2020-05-10 | 2020-05-20 | 0%
1.7.3 | Design Class | 2020-05-21 | 2020-05-24 | 0%
1.7.4 | Design DB | 2020-05-15 | 2020-05-17 | 0%
1.7.5 | Design Architecture | 2020-05-18 | 2020-06-18 | 0%
1.8 | Product Design Document |  |  | 0%
1.9 | Design Tests | 2020-06-01 | 2020-06-03 | 0% | Create a Design Plan
1.9.1 | Design Manual Tests | 2020-06-01 | 2020-06-03 | 0%
1.10 | Test Design Document |  |  | 0%
2 | Kick off Meeting | 2020-05-13 | 2020-06-07 | 0% | No dependency
2.1 | Develop Product Backlog | 2020-05-13 | 2020-06-07 | 0%
2.1.1 | User Stories Correction | 2020-05-13 | 2020-05-13 | 0%
2.1.2 | Written product backlog | 2020-06-04 | 2020-06-06 | 0%
2.1.3 | Feedback and closure | 2020-06-07 | 2020-06-07 | 0%
2.2 | Product Backlog |  |  | 0%
3 | Working Envoimment Setup | 2020-06-08 | 2020-06-10 | 0% | No dependency
3.1 | Setup PC for Development | 2020-06-08 | 2020-06-08 | 0%
3.2 | Setup testing environment | 2020-06-09 | 2020-06-09 | 0%
3.3 | Setup servers | 2020-06-10 | 2020-06-10 | 0%
3.4 | Environment Setup Document |  |  | 0%
4 | Development | 2020-06-19 | 2021-04-28 | 0% | After 1 : Project Planning
4.1 | AI Development | 2020-06-19 | 2021-03-02 | 0%
4.1.1 | Sprint 1 : Data preprocessing | 2020-06-19 | 2020-08-18 | 0%
4.1.1.1 | Daily standup Meeting | 2020-06-19 | 2020-08-18 | 0%
4.1.1.2 | Korean | 2020-06-19 | 2020-08-15 | 0%
4.1.1.3 | Japanese | 2020-06-19 | 2020-08-15 | 0%
4.1.1.4 | French | 2020-06-19 | 2020-08-15 | 0%
4.1.1.5 | Prototype Deployment | 2020-08-16 | 2020-08-17 | 0%
4.1.1.6 | Sprint Review & Retrospective Meeting | 2020-08-18 | 2020-08-18 | 0%
4.1.1.7 | AI developed With Documentation
4.1.2 | Sprint 2 : Feature extraction | 2020-08-19 | 2020-09-29 | 0%
4.1.2.1 | Daily standup Meeting | 2020-08-19 | 2020-09-29 | 0%
4.1.2.2 | Korean | 2020-08-19 | 2020-09-26 | 0%
4.1.2.3 | Japanese | 2020-08-19 | 2020-09-26 | 0%
4.1.2.4 | French | 2020-08-19 | 2020-09-26 | 0%
4.1.2.5 | Prototype Deployment | 2020-09-27 | 2020-09-28 | 0%
4.1.2.6 | Sprint Review & Retrospective Meeting | 2020-09-29 | 2020-09-29 | 0%
4.1.2.7 | AI developed With Documentation
4.1.3 | Sprint 3 : Algorithm and model analysis | 2020-09-30 | 2020-11-10 | 0%
4.1.3.1 | Daily standup Meeting | 2020-09-30 | 2020-11-10 | 0%
4.1.3.2 | Korean | 2020-09-30 | 2020-11-07 | 0%
4.1.3.3 | Japanese | 2020-09-30 | 2020-11-07 | 0%
4.1.3.4 | French | 2020-09-30 | 2020-11-07 | 0%
4.1.3.5 | Prototype Deployment | 2020-11-08 | 2020-11-09 | 0%
4.1.3.6 | Sprint Review & Retrospective Meeting | 2020-11-10 | 2020-11-10 | 0%
4.1.3.7 | AI developed With Documentation
4.1.4 | Sprint 4 : Model optimization | 2020-11-11 | 2020-12-22 | 0%
4.1.4.1 | Daily standup Meeting | 2020-11-11 | 2020-12-22 | 0%
4.1.4.2 | Korean | 2020-11-11 | 2020-12-19 | 0%
4.1.4.3 | Japanese | 2020-11-11 | 2020-12-19 | 0%
4.1.4.4 | French | 2020-11-11 | 2020-12-19 | 0%
4.1.4.5 | Prototype Deployment | 2020-12-20 | 2020-12-21 | 0%
4.1.4.6 | Sprint Review & Retrospective Meeting | 2020-12-22 | 2020-12-22 | 0%
4.1.4.7 | AI developed With Documentation
4.1.5 | Sprint 5 : Model verification | 2020-12-23 | 2021-02-02 | 0%
4.1.5.1 | Daily standup Meeting | 2020-12-23 | 2021-02-02 | 0%
4.1.5.2 | Korean | 2020-12-23 | 2021-01-30 | 0%
4.1.5.3 | Japanese | 2020-12-23 | 2021-01-30 | 0%
4.1.5.4 | French | 2020-12-23 | 2021-01-30 | 0%
4.1.5.5 | Prototype Deployment | 2021-01-31 | 2021-02-01 | 0%
4.1.5.6 | Sprint Review & Retrospective Meeting | 2021-02-02 | 2021-02-02 | 0%
4.1.5.7 | AI developed With Documentation
4.1.6 | Sprint 6 : Performance evaluation | 2021-02-03 | 2021-03-02 | 0%
4.1.5.1 | Daily standup Meeting | 2021-02-03 | 2021-03-02 | 0%
4.1.5.2 | Korean | 2021-02-03 | 2021-02-27 | 0%
4.1.5.3 | Japanese | 2021-02-03 | 2021-02-27 | 0%
4.1.5.4 | French | 2021-02-03 | 2021-02-27 | 0%
4.1.5.5 | Prototype Deployment | 2021-02-28 | 2021-03-01 | 0%
4.1.5.6 | Sprint Review & Retrospective Meeting | 2021-03-02 | 2021-03-02 | 0%
4.1.5.7 | AI developed With Documentation
4.2 | UI/UX Design | 2020-06-19 | 2020-07-18 | 0%
4.2.1 | Sprint 7 : Web Front End | 2020-06-19 | 2020-07-18 | 0%
4.2.1.1 | Daily standup Meeting | 2020-06-19 | 2020-07-18 | 0%
4.2.1.2 | Development and Testing | 2020-06-19 | 2020-07-15 | 0%
4.2.1.3 | Prototype Deployment | 2020-07-16 | 2020-07-17 | 0%
4.2.1.4 | Sprint Review & Retrospective Meeting | 2020-07-18 | 2020-07-18 | 0%
4.2.1.5 | Front End developed With Documentation |  |  | 0%
4.2.2 | Sprint 8 : App Front End | 2020-06-19 | 2020-07-18 | 0%
4.2.2.1 | Daily standup Meeting | 2020-06-19 | 2020-07-18 | 0%
4.2.2.2 | Development and Testing | 2020-06-19 | 2020-07-15 | 0%
4.2.2.3 | Prototype Deployment | 2020-07-16 | 2020-07-17 | 0%
4.2.2.4 | Sprint Review & Retrospective Meeting | 2020-07-18 | 2020-07-18 | 0%
4.2.2.5 | Front End developed With Documentation |  |  | 0%
4.3 | Function Development | 2021-03-03 | 2021-04-02 | 0%
4.3.1 | Sprint 9 : Function | 2021-03-03 | 2021-04-02 | 0%
4.3.1.1 | Daily standup Meeting | 2021-03-03 | 2021-04-02 | 0%
4.3.1.2 | Grammar Correction Function | 2021-03-03 | 2021-03-30 | 0% | After AI development
4.3.1.3 | Pronunciation Correction Function | 2021-03-03 | 2021-03-30 | 0% | After AI development
4.3.1.4 | Shadowing Contents Function | 2021-03-03 | 2021-03-30 | 0%
4.3.1.5 | Level Test Function | 2021-03-03 | 2021-03-30 | 0%
4.3.1.6 | User Matching Function | 2021-03-03 | 2021-03-30 | 0%
4.3.1.7 | Prototype Deployment | 2021-03-31 | 2021-04-01 | 0%
4.3.1.8 | Sprint Review & RetrospectiveMeeting | 2021-04-02 | 2021-04-02 | 0%
4.3.1.9 | Function developed With Documentation
4.4 | Database Development | 2021-03-29 | 2021-04-28 | 0% | No dependency
4.4.1 | Sprint 10 : Setup Database | 2021-03-29 | 2021-04-28 | 0%
4.4.1.1 | Daily standup Meeting | 2021-03-29 | 2021-04-28 | 0%
4.4.1.2 | Development | 2021-03-29 | 2021-04-25 | 0%
4.4.1.3 | Testing | 2021-04-19 | 2021-04-25 | 0%
4.4.1.3.1 | System Testing | 2021-04-19 | 2021-04-25 | 0%
4.4.1.4 | Deployment | 2021-04-26 | 2021-04-27 | 0%
4.4.1.5 | Sprint Review & Retrospective Meeting | 2021-04-28 | 2021-04-28 | 0%
4.4.1.6 | Database Module of user tracking is developed |  |  | 0%
5 | Production Testing & Deployment | 2021-04-29 | 2021-05-15 | 0% | After 4 : Development
5.1 | Testing | 2021-04-29 | 2021-05-08 | 0%
5.1.1 | Integration test | 2021-04-29 | 2021-05-05 | 0%
5.1.2 | Quality management and feedback | 2021-05-06 | 2021-05-08 | 0%
5.1.3 | Test Report
5.2 | Deployment | 2021-05-09 | 2021-05-15 | 0%
5.2.1 | Create and share scenario | 2021-05-09 | 2020-05-10 | 0%
5.2.2 | Notice | 2020-05-10 | 2020-05-10 | 0%
5.2.3 | Deployment/Preparing of Failover | 2020-05-11 | 2020-05-13 | 0%
5.2.4 | Server Transfer | 2021-05-14 | 2021-05-15 | 0%
5.2.5 | Deployment Report |  |  | 0%
6 | Project Closing | 2021-05-16 | 2021-05-25 | 0% | After 5 : Production Testing & Deployment
6.1 | Execute Closing procedure | 2021-05-16 | 2021-05-25 | 0%
6.2 | Project Delievered |  |  | 0%